## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce | Latest Update
1 | 2024-10-10 | Jason L | P5 | Closed | Jason L | Multiple game level stages | Game should switch to the next game level stage upon completing the current stage. | As of M2s completion, we currently have designed one basic game room | Create mutiple game stages that we switch between each with new wall textures, game backgrounds, and game difficulty, | Multiple game levels have been implemented in M3.
2 | 2024-10-10 | Jason L | P5 | Closed | Sean F | Game power ups like heal potions, Invincibility, etc. | Have power ups spawn around the game level which can be activated instantly upon picking it up. | As of M2s completion, we have not implemented all power ups | Create power up sprites and associate sprites with player stats | Mouse gesture power-ups for healing have been implemented in M3.
3 | 2024-10-11 | Jason L | P4 | Closed | Abhigyan D | Have multiple enemies spawn | Mutliple enemies should be able to spawn around the game room randomly | As of M1s completion, we have implemented one enemy with pathfinding AI | Implement changes to the code that allow for mutiple enemies to spawn at random locations periodically | Multiple game enemies have been implemented in M2.
4 | 2024-10-12 | Jason L | P5 | Closed | William C | Create different enemy types like bosses | There should be different enemy types in the game aside from the normal enemy. Boss enemies should do more damage and have more health as well. | As of M2s completion, we only have two enemy types (melee and range) - need to create bosses | Add another enemy type into the code that has more health and deals more damage than the normal enemy, along with different features and graphics | A new boss enemy type has been implemented for M3.
5 | 2024-10-12 | Jason L | P5 | Won't Fix | Maysam F | Have enemies be able to damage each other | Enemy bullets should be able to damage other enemies along with the player | As of M2s completion, the enemy is only able to damage the player and vice versa. | Implement mutiple enemies into the game and allow their bullets to deduct health points from each other upon collision. Essentially, allow for "friendly fire" between enemies. | The team decided this is no longer a good idea as it may lead to confusion for players and make the game easier.
6 | 2024-10-12 | Jason L | P5 | Closed | Jason L | Improve upon current game sprites | Player, enemy, wall sprites should be detailed and representative of the final product | As of M1s completion, we have a blue circle for the player, red circle for the enemy, and a wall sprite placeholder. | Design new sprites that will replace the placeholders we are currently using and incorparate them into the game. | Improved sprites were designed and integrated into the game in M2.
7 | 2024-10-12 | Jason L | P5 | Closed | Abhigyan D | Player health bar to indicate remaining player health | A health bar should appear in the top left corner of the game screen to indicate how much health the player has remaining. | As of M2s completion, the players health is not displayed through a health bar but is rather behind code. | Create a visible health bar in-game and associate it with the players current health to indicate their current health percentage. | Character health bars were implemented in M3.
8 | 2024-10-13 | Abhigyan D | P4 | Closed | Abhigyan D | No death animation when player dies, automatically resets | Ideally, the game should show a "You died" screen with their score and an option to play again. | As of M1's completion, the game simply resets, which does not give players much feedback on their loss. | Move close to the enemy and let the enemy shoot the player down. The game will simply reset upon death. | Sound effects and death screen were implemented in M2.
9 | 2024-10-13 | Sean F | P4 | Closed | Sean F | No Start menu and Tutorial Screen | When you first open the game, you should be presented with a screen containing buttons for Start Game, How to Play, and Exit | The game begins as soon as you run the executable | Run the game. | Different game screens were implemented in M2.
10 | 2024-10-13 | Sean F | P4 | Won't Fix | William C | No Guideline for aim | When you have your cursor anywhere on the game screen, a translucent guideline originating from the player that extends up to the first collision, then extends in the direction of reflection should always appear. This would help players plan out their lasers easier. | Moving your cursor around shows no guideline | Placing the cursor anywhere on the game screen demonstrates the lack of guide line. | Aim guidelines were no longer a priority for the game.
11 | 2024-11-02 | Abhigyan D | P5 | Won't Fix | Abhigyan D | Point system not implemented | In the game screen, we should see the player's points based on either the amount of kills they've gotten or the levels they have cleared. | As of M2s completion, we have not yet decided or implemented any point system, so the points stay static at 0. | Play the game - regardless of user actions the points will not be incremented or decremented. | The point system has been discarded and no longer a priority for the game - the player's goal is to win the game by defeating all enemies.
12 | 2024-11-02 | Abhigyan D | P4 | Won't Fix | Maysam F | No wall sliding | When the player is against the game walls, and multiple WASD keys are being pressed, the player should slide against the walls moving in the direction there is more space. | As of M2s completion, the player will get stuck on the wall if clicking multiple keys, needing to release some key to continue moving in the desired direction. | Move towards the middle of the right boundary of the game and click both W and D simultaneouly. Although going further right should be limited, the player should still slide upwards as there is space - instead you will see the player get stuck on the wall. | Wall sliding is no longer a priority for the game.
13 | 2024-11-19 | Abhigyan D | P5 | Open | Maysam F | Repetitive room design | Different game levels should have randomized or designed obstacles that make the game more interesting | As of M3s completion, each level uses the same room layout, which can get boring for players. | Simply play the game, progress through levels, and notice the similar rooms across levels.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release